## Cover
Template
TEST PLAN
Document Code
| Version | 3.3
| Effective Date | 2022-07-15

## Table of Content
TABLE OF CONTENT
1 | INTRODUCTION | Click here
1.1 | Purpose
1.2 | Definitions, Acronyms, and Abbreviations
1.3 | References
1.4 | Background information
1.5 | Scope of testing
1.6 | Constraints/Assumptions
1.7 | Risk/Opportunity list
1.8 | Staff & Training Management
2 | REQUIREMENT FOR TEST | Click here
2.1 | Test items
2.2 | Acceptance Test Criteria
3 | TEST STRATEGY | Click here
3.1 | Test types
3.2 | Test stages
4 | REVIEW STRATEGY | Click here
5 | STAFF & TRAINING MANAGEMENT | Click here
5.1 | Human Resource
5.2 | Test management
5.3 | Training Management
6 | TEST ENVIROMENT | Click here
6.1 | Hardware
6.2 | Software
6.3 | Infrastructure
7 | TEST CONFIGURATION | Click here
7.1 | Hardware configuration
7.2 | Software configuration
8 | TEST MILESTONES | Click here
9 | DELIVERABLES | Click here
10 | TEST SCHEDULE | Click here
11 | RISK & OPPORTUNITY | Click here
12 | RECORD OF CHANGE | Click here

## 1. Introduction
1 | INTRODUCTION
1.1 | Purpose
<Describe briefly about the purpose and organization of the documents. How many sections? What each section describes about?>
1.2 | Definitions, Acronyms, and Abbreviations
<This subsection provides the definitions of all terms, acronyms, and abbreviations required to properly interpret the Test Plan>
| No | Abbreviations | Description | Note
| 1 | AT | Acceptance test
| 2 | B Voucher | Bug voucher
| 3 | DMS | Defect Management System (Fsoft tool)
| 4 | ES | Enhance Specification
| 5 | IT | Integration test
| 6 | PM | Project Manager
| 7 | PTL | Project Technical Leader
| 8 | PT/TT | Program test/ Total test
| 9 | P Voucher | Program voucher
| 10 | QA | Quality Assurance
| 11 | QUP | Quality up
| 12 | SRS | Software Requirement Specification
| 13 | ST | System test
| 14 | TP | Test Plan
| 15 | TC | Test Case
| 16 | TR | Test Report
| 17 | UAT | User Acceptance test
| 18 | UT | Unit test
| 17 | akaAT | All-in-one Automation Test Solution. Tester can build sophisticated tests for Web, Desktop, and Mobile without a ... line of code.
| 18 | ART | Automated Regression Testing is a web portal that helps build user interactive scenarios and automate repetitive execution on computers, mobiles, or other devices.
| 17 | ATOMP | An Automation test tool in mobile testing industry
1.3 | References
<This subsection provides a complete list of all documents referenced elsewhere in the Test Plan. Identify each document by title, Author, Version and Effective date>
| No | Title/File name | Author | Version | Effective Date
1
2
3
1.4 | Background information
<Enter a brief description of the target-of-test (components, application, system, etc.) and its goals. Include the information such as major functions and features, its architecture, and a brief history of the project.
Refer to Guideline Test Plan for sample>
1.5 | Scope of testing
<Describe the stages of testing­ - for example, Unit, Integration, or System - and the types of testing that will be addressed by this plan, such as Function or Performance.
Provide a brief list of Test types.
List any assumptions made during the development of this document that may impact the design or execution of testing (for example: browsers – if customer not requests directly, can assume to execute test in iE, not Netscape).
The defects found are in range of defect expectation (refer to Planned defect in Fsoft Insight)
Describe generally about the functions or special cases which will not in scope of testing. For example, because Performance testing and capacity planning for new systems are out of scope, non functional requirement …
Refer to Guideline Test Plan for sample
1.6 | Constraints/Assumptions
<Address any constraints/Assumptions on testing. They may be:
- Test environment difference or lack of some external systems that interface to the system-under-test (Reference to SRS document may be included here if the constraints have been stated in SRS)
- Constraints/Assumptions on resource, schedules, lack of tools, etc.
Refer to Guideline Test Plan for sample>
1.7 | Risk/Opportunity list
<Refer sheet 11. Risk & Opportunity>
1.8 | Staff & Training Management
<Refer sheet 5. Staff & Training Management>

## 2. Requirement for test
2 | REQUIREMENT FOR TEST
2.1 | Test items
<The listing below identifies those items (use cases, functional requirements, non-functional requirements) that have been identified as targets for testing. This list represents what will be tested and the number of test case estimated for testing each item.
Enter a high level list of features and functions to be tested/not tested. Refer to the sample in Guideline Test Plan>.
Repository
https://hcm-svn.fsoft.com.vn/svn/<Project>/<Parent_Folder>/<Test_Item>/
Revision: <SVN Revision>
The table below can be used if suitable.
| No | Name of features and functions | Outline of features and functions | Number of Test case(Estimate) | Can be automated (Yes/No) | Note
2.2 | Acceptance Test Criteria
<List of criteria which are based on to accept the products, for example:
- All planned test cases have been executed
- All found defects have been analysis and give out solution
- All the defect related test cases have been re-executed and all known defects have been fixed, and no new defects have been discovered
- No open critical/major defects
- ….
Refer to the sample in Guideline Test Plan>

## 3. Test strategy
3 | TEST STRATEGY
<The Test Strategy presents the recommended approach to the testing of the target-of-test. Outline for test strategy, refer to Guideline Test Plan. >
3.1 | Test types
3.1.1 Static Testing
< Static Testing is used as a complement method for Dynamic Testing. During static testing, software work products are examined manually, or with a set of tools (Sonar Quebe, Corverity, BlackDuck, ...), but not executed. Types of defects that are easier to find during static testing are: deviations from standards, missing requirements, design defects, test documentation defects, non-maintainable code and inconsistent interface specifications. List down static techniques will be used in the project: - Review: Informal Review, Walkthrough, Technical Review, Inspection - Static analysis by tool to check Coding Standards, Code metrics, Code Structure Detail of Review strategy refers to part 4. Review Strategy in this document & Project Plan document, section Quality Management Detail of Static analysis by tool refers to Project Plan document, section Quality Management >
3.1.2 Unit Testing
<Unit testing involves testing individual pieces of code. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Ensure the unit operates as specified in the unit design>
| Technique: | <Black box testing assesses a system solely from the outside, without the operator or tester knowing what is happening within the system to generate responses to test actions> <White box testing is an approach that allows testers to inspect and verify the inner workings of a software system—its code, infrastructure, and integrations with external systems> <Gray box testing is used to execute test suites, test methods, test cases and performing risk analysis> <Use UT test tool (ex: Diffblue, DevMate, …)>
| Completion Criteria: | <All planned tests have been executed>
<All identified defects have been addressed and closed> <Achieving a certain level of code coverage>
Special Considerations:
3.1.3 Function Testing
3.1.3.1 Function Testing
< Function testing of the target-of-test should focus on any requirements for test that can be traced directly to use cases or business functions and business rules. For more details, refer to the sample in Guideline Test Plan. >
| Test Objective: | <Ensure proper target-of-test functionality, including navigation, data entry, processing, and retrieval. >
| Technique: | <Execute each use case, use-case flow, or function, using valid and invalid data, to verify the following:
- The expected results occur when valid data is used.
- The appropriate error or warning messages are displayed when invalid data is used.
- Each business rule is properly applied.
- Use Automation test tool (ex: akaAT, ART, ATOMP, …)>
| Completion Criteria: | - <All planned tests have been executed.
- All identified defects have been addressed and closed>
| Special Considerations: | <Identify or describe those items or issues (internal or external) that impact the implementation and execution of function test>
3.1.3.2 Business Cycle Testing
<Outline for Business Cycle Testing. Refer to the sample in Guideline Test Plan>
| Test Objective | <Ensure proper target-of-test and background processes function according to required business models and schedules. >
| Technique: | <Testing will simulate several business cycles by performing the following:
The tests used for target-of-test’s function testing will be modified or enhanced to increase the number of times each function is executed to simulate several different users over a specified period.
All time or date-sensitive functions will be executed using valid and invalid dates or time periods.
All functions that occur on a periodic schedule will be executed or launched at the appropriate time.
Testing will include using valid and invalid data to verify the following:
The expected results occur when valid data is used.
The appropriate error or warning messages are displayed when invalid data is used.
Each business rule is properly applied.
Use Automation test tool (ex: akaAT, ART, ATOMP, …)
| Completion Criteria: | <All planned tests have been executed.
All identified defects have been addressed.>
| Special Considerations: | <System dates and events may require special support activities
Business model is required to identify appropriate test requirements and procedures. >
3.1.4 User Interface Testing
< User Interface (UI) testing verifies a user’s interaction with the software. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Verify the following:
Navigation through the target-of-test properly reflects business functions and requirements, including window-to-window, field-to-field, and use of access methods (tab keys, mouse movements, accelerator keys)
Window objects and characteristics, such as menus, size, position, state, and focus conform to standards. >
| Technique: | <Create or modify tests for each window to verify proper navigation and object states for each application window and objects.
| Completion Criteria: | <Each window successfully verified to remain consistent with benchmark version or within acceptable standard>
| Special Considerations: | <Not all properties for custom and third party objects can be accessed. >
3.1.5 Data and Database Integrity Testing
< The databases and the database processes should be tested as a subsystem within the Project. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Ensure database access methods and processes function properly and without data corruption. >
| Technique: | <Invoke each database access method and process, seeding each with valid and invalid data or requests for data.
Inspect the database to ensure the data has been populated as intended, all database events occurred properly, or review the returned data to ensure that the correct data was retrieved for the correct reasons>
| Completion Criteria: | <All database access methods and processes function as designed and without any data corruption. >
| Special Considerations: | <Testing may require a DBMS development environment or drivers to enter or modify data directly in the databases.
Processes should be invoked manually.
Small or minimally sized databases (limited number of records) should be used to increase the visibility of any non-acceptable events. >
3.1.6 Performance testing
3.1.6.1 Performance testing
<Performance test is to measure and evaluate response times, transaction rates, and other time-sensitive requirements. It includes Load test, Stress test, Volume test… For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Verify performance behaviors for designated transactions or business functions under the following conditions:
normal anticipated workload
anticipated worst case workload>
| Technique: | <Use Test Procedures developed for Function or Business Cycle Testing.
Modify data files to increase the number of transactions or the scripts to increase the number of iterations each transaction occurs.
Scripts should be run on one machine (best case to benchmark single user, single transaction) and be repeated with multiple clients (virtual or actual, see Special Considerations below). >
| Completion Criteria: | <Single Transaction or single user: Successful completion of the test scripts without any failures and within the expected or required time allocation per transaction.>
<Multiple transactions or multiple users: Successful completion of the test scripts without any failures and within acceptable time allocation. >
| Special Considerations: | <Comprehensive performance testing includes having a background workload on the server.
There are several methods that can be used to perform this, including:
“Drive transactions” directly to the server, usually in the form of Structured Query Language (SQL) calls.
Create “virtual” user load to simulate many clients, usually several hundred. Remote Terminal Emulation tools are used to accomplish this load. This technique can also be used to load the network with “traffic”.
Use multiple physical clients, each running test scripts to place a load on the system.
Performance testing should be performed on a dedicated machine or at a dedicated time. This permits full control and accurate measurement.
The databases used for Performance Testing should be either actual size or scaled equally. >
3.1.6.2 Load Testing
<Load testing is a performance test which subjects the target-of-test to varying workloads to measure and evaluate the performance behaviors and ability of the target-of-test to continue to function properly under these different workloads. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Verify performance behavior time for designated transactions or business cases under varying workload conditions. >
| Technique: | <Use tests developed for Function or Business Cycle Testing.
Modify data files to increase the number of transactions or the tests to increase the number of times each transaction occurs. >
| Completion Criteria: | <Multiple transactions or multiple users: Successful completion of the tests without any failures and within acceptable time allocation. >
| Special Considerations: | <Load testing should be performed on a dedicated machine or at a dedicated time. This permits full control and accurate measurement. The databases used for load testing should be either actual size or scaled equally. >
3.1.6.3 Stress Testing
<Stress testing is a type of performance test implemented and executed to find errors due to low resources or competition for resources. For more details, refer to the sample in Guideline Test Plan >
<Note: References to transactions below refer to logical business transactions. >
| Test Objective: | <Verify that the target-of-test functions properly and without error under the following stress conditions:
little or no memory available on the server (RAM and DASD)
maximum actual or physically capable number of clients connected or simulated multiple users performing the same transactions against the same data or accounts worst-case transaction volume or mix (see Performance Testing above).
Notes: The goal of Stress Testing might also be stated as identify and document the conditions under which the system FAILS to continue functioning properly. >
| Technique: | <Use tests developed for Performance Profiling or Load Testing.
To test limited resources, tests should be run on a single machine, and RAM and DASD on server should be reduced or limited.
For remaining stress tests, multiple clients should be used, either running the same tests or complementary tests to produce the worst-case transaction volume or mix.
| Completion Criteria: | <All planned tests are executed and specified system limits are reached or exceeded without the software failing or conditions under which system failure occurs is outside of the specified conditions. >
| Special Considerations: | <Stressing the network may require network tools to load the network with messages or packets.
The DASD used for the system should temporarily be reduced to restrict the available space for the database to grow.
Synchronization of the simultaneous clients accessing of the same records or data accounts. >
3.1.6.4 Volume Testing
< Volume Testing subjects the target-of-test to large amounts of data to determine if limits are reached that cause the software to fail. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | <Verify that the target-of-test successfully functions under the following high volume scenarios:
Maximum (actual or physically- capable) number of clients connected, or simulated, all performing the same, worst case (performance) business function for an extended period.
Maximum database size has been reached (actual or scaled) and multiple queries or report transactions are executed simultaneously. >
| Technique: | <Use tests developed for Performance Profiling or Load Testing.
Multiple clients should be used, either running the same tests or complementary tests to produce the worst case transaction volume or mix (see Stress Testing above) for an extended period.
Maximum database size is created (actual, scaled, or filled with representative data) and multiple clients used to run queries and report transactions simultaneously for extended periods. >
| Completion Criteria: | <All planned tests have been executed and specified system limits are reached or exceeded without the software or software failing. >
| Special Considerations: | <What period of time would be considered an acceptable time for high volume conditions, as noted above? >
3.1.7 Security and Access Control Testing
< Outline for Security and Access Control Testing, refer to the sample in Guideline Test Plan >
| Test Objective: | Application-level Security: <Verify that an actor can access only those functions or data for which their user type is provided permissions. >
System-level Security: Verify that only those actors with access to the system and applications are permitted to access them. >
| Technique: | Application-level Security: <Identify and list each user type and the functions or data each type has permissions for. >
<Create tests for each user type and verify each permission by creating transactions specific to each user type. >
Modify user type and re-run tests for same users. In each case, verify those additional functions or data are correctly available or denied.
System-level Access: <See Special Considerations below>
| Completion Criteria: | <For each known actor type the appropriate function or data are available, and all transactions function as expected and run in prior Application Function tests. >
| Special Considerations: | <Access to the system must be reviewed or discussed with the appropriate network or systems administrator. This testing may not be required as it may be a function of network or systems administration. >
3.1.8 Regression Testing
<Regression testing is a necessary maintenance activity aimed at showing that code has not been adversely affected by changes. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | Regression testing is to validate modified parts of the software, to make sure that the modification does not cause errors in other parts.
| Technique: | <Reuse the set of test cases from an existing test suite to test a modified module>.
<Use Automaton test tool (ex: akaAT, ART, ATOMP, …): Creating some functional test scripts. Define automated test execution schedule here >
< 80% Test cases is randomly select from existing Test cases >
< Construct a program-analysis infrastructure. We are building an extensible infrastructure to implement and evaluate a program-analysis. Basing on the analysis result, we identify scope of regression test>
| Completion Criteria: | <All test cases are performed and passed>
<All selected test cases are performed and passed>
Special Considerations:
3.1.9 Interfaces or connections testing
<Describe the Interfaces or connections which projects will use for testing. For more details, refer to the sample in Guideline Test Plan >
| Test Objective: | Interface or Connection Testing is done -To ensure that end-users or customer should not encounter any problem when using a particular software product -To identify which application areas are usually accessed by end-users and to check its user-friendliness as well. -To verify security requirements while communication propagates between the systems -To check if a solution is capable to handle network failures between an application server and website
| Technique: | <Create the set of test cases to make sure Workflow: It ensures that the Interface or Connection engine handles your standard workflows as expected. Edge cases -unexpected values: This is considered when testing include date, month and day reversed. Performance, load, and network testing: A high-volume Interface or Connection may require more Load Testing than a low-volume Interface or Connection, depending on the Interface or Connection engine and connectivity infrastructure Individual systems: This includes testing each system individually. For example, billing system and inventory management system for the retail store should be able to operate separately.>
| Completion Criteria: | <All test cases are performed and passed>
<All selected test cases are performed and passed>
Special Considerations:
3.2 | Test stages
<Clearly state the stage/level in which the test will be executed. Identified below are the stages in which common test are executed. Recommended Entry/Suspension/Resumption/Exit Criteria are listed, base on the project characteristics, they could be adjusted accordingly>
| Test level | Main tasks | Entry Criteria | Suspension Criteria | Resumption Criteria | Exit Criteria
| Unit Test | - Verifying that the unit operates as specified in the unit design - Achieving a certain level of code coverage | - System design, technical design and other relevant documents are properly reviewed, analyzed and approved. - Business and functional requirements are defined and approved. - Testable codes or units are available. - Availability of test environment. | - The build contains many serious defects which seriously or limit testing progress. - Significant change in requirements suggested by client - Software/Hardware problems - Assigned resources are not available when needed by test team | - Issue due to which suspension occurs gets resolved. | - Successfully executed the unit tests. - Priority bugs are fixed and closed. - Project code is complete.
| Integration Test | - Verifying that the units together operate as specified in the global design - Verifying that the interfaces operate as specified in the interface specification | - Completion of unit testing phase. - Priority bugs found during unit testing has been fixed and closed. - Integration plan and test environment to carry out integration testing is ready. - Each module has gone through unit testing before the integration process - Test cases, test scripts, test data is ready | - The build contains many serious defects which seriously or limit testing progress. - Significant change in requirements suggested by client - Software/Hardware problems - Assigned resources are not available when needed by test team | - Issue due to which suspension occurs gets resolved. | - No Outstanding critical defects. - All priority bugs are fixed and closed. - Integration system has passed the functional and performance requirements. - Install-ability has been verified.
| System Test | - Verifying that the system operates as specified in the requirements specification - Achieving a certain level of system requirements coverage | - Successful completion of integration testing process. - Priority bugs found during previous testing activities has been fixed and closed. - System testing environment is available. - Test cases, test scripts, test data is ready | - The build contains many serious defects which seriously or limit testing progress. - Significant change in requirements raised by client - Software/Hardware problems - Assigned resources are not available when needed by test team | - Issue due to which suspension occurs gets resolved. | - All planned Test Cases have been executed i.e. 100% functionality is tested - At least 95% system test cases have to be passed - 100% high priority test cases passed. - Only Medium and Cosmetic defects can be accepted
| Acceptance Test | - Verifying that the system satisfies defined acceptance criteria - Validating whether the system is ‘fit for use’ - Achieving a certain level of user requirements coverage | - All the inputs of system testing are baseline and approved by relevant stakeholders (Common requirement, ADD, SRS, Design, Notes app, software package, and System test cases) - System testing is done and all known issues (if any) are aware by relevant stakeholders (Dev lead, SDC, Regional leads) and documented in release notes and delivered with the build. - System test results are prepared. PASS conclusion is stated clearly in the report and approved by Test lead. | - The build contains many serious defects which seriously or limit testing progress. - Significant change in requirements suggested by client - Software/Hardware problems - Assigned resources are not available when needed | - Issue due to which suspension occurs gets resolved. | - Successful execution of the user acceptance tests. '- Approval from management to stop UAT. - Business requirements got fulfilled. - 100% found bugs are fixed, remaining bugs must be confirmed by customer. - Signing off acceptance testing.
| Type of Tests | Stage of Test
|  | Unit | Integration | System | Acceptance
| <Static Test> | X | X | X | X
| <Function Test > | X | X | X | X
| <User Interface test> | X | X | X
| <Performance Tests |  |  | X | X
(Performance profiles of individual components)>
| <Load, Stress, Volume test> |  |  | X | X
| <Security test> |  | X | X
| <Date integrity test> |  | X | X | X
3.3 | Automation test strategy
- Solution for automaton test: + Select the right automation test tool + Select modules for automated + Build automation test team Refer to Guideline_Automation Testing
- Automation test goal: Determine the rate for automation test
- Test case selection policy: Normally, not all test cases can be automated so automation team need to evaluate and define which parts of test cases can be automated, which parts cannot, and which parts should be done first, which part should be automated later.
| Should automate |  | Should not automate or Low priority
| - High risk - Business critical test cases - Test cases that are executed repeatedly - Test cases that are very tedious or difficult to perform manually - Test cases which are time consuming and need multiple data sets. |  | - Test cases that are newly designed and not executed manually at least once - Test cases for which the requirements are changing frequently - Test cases which are executed on ad-hoc basis - Test cases that are extremely complex

## 4. Review strategy
4 | REVIEW STRATEGY
<The Review Strategy presents the recommended approach to the testing documents of the target-of-test. Note that if test basic documents (Requirement Specification, User Story…) are planned for review in Project Plan document - section Quality Management then they shouldn't be included here >
| No | Review Item | Reviewer | Review Type | Review Method | Selection Criteria | Entry Criteria | Suspension Criteria | Resumption Criteria | Completion Criteria
| 1 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> |  | <Technical review> | <Checklist or not> | Technical document should be selected such as SRS, HLD, DD, test plan | Pass previous review (Group review, Peer review) | After 30 minutes of checking, on average more than 3 critical and/or major defects are found per page | - Issues of previous review are fixed and closed - Entry criteria is met | <Pass Checklist, Related defects are closed>
| 2 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> | <Owner> | <Self-review> | <Checklist or not Tools used or not> | All test documentation | - The document author completes and confident with the quality of document - The document has been cleaned up by running any automated checks that apply | - | - | <Pass Checklist, Related defects are closed Fix all comment of Tools>
| 3 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> | <People has similar skill> | <Peer-review> | <Checklist or not Tools used or not> | Members who are in-charge of related functions will be assigned peer review work product of each other | Self-review is passed by the document author using checklist | On average more than 6 critical and/or major defects are found per page | - Issues of previous review are fixed and closed - Entry criteria is met | <Pass Checklist, Related defects are closed Fix all comment of Tools>
| 4 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> |  | <Informal-review> | <Checklist or not Tools used or not> | Work product of inexperience member will be reviewed by experience one | The document author is confident with the quality of document | - | - | <Pass Checklist, Related defects are closed Fix all comment of Tools>
| 5 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> | <QA> | <Inspection> | <Checklist or not Tools used or not> | All deliverables to customer must be inspected | - Pass previous review (Group review, Technical review) - All necessary supporting documentations needed for the inspection are stable and available | On average more than 3 critical and/or major defects are found per page | - Issues of previous review are fixed and closed - Entry criteria is met | <Pass Checklist, Related defects are closed Fix all comment of Tools>
| 6 | <work product to be reviewed (Requirement Specification, User Story, Test Plan, Unit test case, Unit test report, Integration test case, Integration test report, System test case, System test report, Test script, Defects...> |  | <Group review> | <Checklist or not> | Important work product should be selected such as Test Design, Test Case, Test Data, Test Report | Self-review is passed by the document author using checklist | After 30 minutes of checking, on average more than 3 critical and/or major defects are found per page | - Issues of previous review are fixed and closed - Entry criteria is met | <Pass Checklist, Related defects are closed>

## 5. Staff & Training Management
5 | STAFF & TRAINING MANAGEMENT
5.1 | Human Resource
This table shows the staffing assumptions for the project.
| Worker/Doer | Role | Specific Responsibilities/Comments | Qualification | % Allocate | Start date | End date | Location
| <Test Leader ‘s Name> | <Test Leader> | <Manage Test resource and assign test tasks> | - <-3 years in Tester Leader Role - Pass ISTQB Advanced certification - Pass PMF certification - Pass Automation Test Foundation> | <100> | <dd/mm/yyyy> | <dd/mm/yyyy> | < Fsoft, Vietnam>
| <Mail account> |  | <Create TP>
<Review TC>
<Create Test report>
| <Tester 1 ‘s Name> | <Tester > | <Create TC/ test scripts/ test suites for modules …> | - <2 years in Tester Role - Pass ISTQB Advanced certification - Pass Automation Test Foundation> | <50> | <dd/mm/yyyy> | <dd/mm/yyyy> | < Fsoft, Vietnam>
| <Mail account> |  | <Execute test/ Run test scripts/ test suites>
<Report test result>
| <Tester 2’s Name> | <Tester > | <Create TC for modules … > | - <College graduates> | <25> | <dd/mm/yyyy> | <dd/mm/yyyy> | < Fsoft, Vietnam>
| <Mail account> |  | <Execute test>
<Report test result>
5.2 | Test management
<Define about the following items’ method:
Test management (Test planning and tracking, Communication)
Defect management (Defect management tool and defect process follow……)
Automation test management (Automation test management tool) >
Refer to the sample in Guideline Test Plan
5.3 | Training Management
5.3.1 | Needed Knowledge & Skill
| # | Knowledge/Skill |  | Required for Role(s) |  |  | Action | # of hour | Provider | Note
| 1 | Create test plan |  | Test leader |  |  | On job Training
| 2 | Create test case |  | Tester |  |  | On job Training
| 3 | Execute test |  | Tester |  |  | On job Training
| 4 | Automation software test |  | Tester |  |  | Class Training
| 5 | …
5.3.2 | Individual Training Plan
<Define Individual Training Plan for team members>
| No | Name |  | <Training Course 1> |  | <Training Course 2> |  | <Training Course 3> |  | <Training Course 4> | Note
1
2
3
4
5
6
7
8
9
10

## 6. Test enviroment
6 | TEST ENVIRONMENT
<List of required hardware and software resources. Describe equipment which needs for testing such as USB Memory, Memory card…etc. Describe the number of equipment need and the duration using these equipment. >
6.1 | Hardware
<Describe the hardware which projects will use for testing
Refer to the sample in Guideline Test Plan>
6.2 | Software
<Describe the software which projects will use for testing
Refer to the sample in Guideline Test Plan>
6.3 | Infrastructure
<List tools will be employed for this project.
Refer to the sample in Guideline Test Plan>
| Purpose | Tool | Vendor/In-house | Version
| <Defect log> | <DMS2> | <Fsoft tool> | <1.4>
| <Test effort> | <Timesheet> | <Fsoft tool> | <3.8.4>
| <Automation test> | <akaAT/ ART/ ATOMP> | <Fsoft tool> | <...>
| <Unit test tools> | <Junit/Cunit/Diffblue/ DevMate> | <Fsoft tool> | <...>

## 7. Test configuration
7 | TEST CONFIGURATION
7.1 | Hardware configuration
7.1.1 HW_CFG_001
<Describe briefly about the HW configuration 1>
| Setting | Value | Remark
| <Switch 1> | <On/Off> | <>
| <Jumper x> | <On/Off> | <>
7.1.2 HW_CFG_002
<Describe briefly about the HW configuration 2>
| Setting | Value | Remark
7.2 | Software configuration
7.2.1 SW_CFG_001
<Describe briefly about the SW configuration 1>
| Setting | Value | Remark
| <Setting 1> | <Value 1> | <>
| <Setting 1> | <Value 1> | <>
7.2.2 SW_CFG_002
<Describe briefly about the SW configuration 2>
| Mode | Value | Remark
| <Setting 1> | <Value 1> | <>
| <Setting 1> | <Value 1> | <>
7.2.3 Automation test tool configuration
<Describe briefly about the automation test tool configuration>
| Setting | Value | Remark
| <Setting 1> | <Value 1> | <>
| <Setting 1> | <Value 1> | <>

## 8. Test milestones
8 | TEST MILESTONES
<Separate test milestones, which should be identified to communicate project status accomplishments>
| Milestone Task | Effort (pd) | Start Date | End Date
| <Create Unit Test Plan> |  | <YY-MM-DD> | <YY-MM-DD>
<Review & update UTP>
<Create Unit Test case/ Unit Test script>
<Review & update UTC/ Unit Test script>
<Create Test Plan>
<Review & update TP>
<Create Integration Test case/ Test script>
Review & Update Integration TC/ Test script>
<Create System Test case/ Test script>
<Review & Update System TC/ Test script>
<Execute Unit Test/ Run Unit test script>
<Execute Integration test/ Run Intergration test script>
<Execute System test/ Run System test script>>

## 9. Deliverables
9 | DELIVERABLES
<Define delivery of Testing. Refer to Project Plan for more details.>.
| No | Product ID | Deliverables | Language | Delivered Date
| 1 | <UT-TP-001> | <Unit Test Plan> | <Japanese> | <YY-MM-DD>*
| 2 | <UT-TP-002> | <Test Plan>
| 3 | <UT-TC-003> | <Unit Test Cases/ Unit Test Scrpts>
| 4 | <IT-TC-003> | <Integration Test Cases/ Integration Test Scripts>
| 5 | <ST-TC-003> | <System Test Cases/ System Test Scripts>
| 6 | <ST-TPR-001> | <Test Procedure Specification/ Test Suite>
| 7 | <UT-DF-003> | <Defect log>
| 8 | <UT-TR-003> | <Test reports>
Note: * <YY-MM-DD> is only used when customer is Japanese.
Content guideline in <> must be deleted when finish test plan.
Product ID will be tracked in case performing Review, Acceptance Test Activity

## 10. Test schedule
10 | TEST SCHEDULE
The Test Schedule is weekly updated by the Project Manager/Tester Leader/Tester Manager.
|  |  |  | Plan |  |  | Actual
| No. | Parent Task | Sub Task | Start Date | End Date | Effort (ph) | Start Date | End Date | Effort (ph) | Remain Effort (h) | PIC | %Complete
| 1 | <Setup Environment> | [9 empty] | 100%
| 2 |  | <JDK, JRE> | [8 empty] | 100%
| 3 |  | <TestNG, Eclipse> | [8 empty] | 100%
| 4 |  | <Unit Test tool>
| 5 |  | <Automation test tool>
| 6 |  | …..
| 7 | <Module1>
| 8 |  | <Study SRS>
| 9 |  | <Design test case>
| 10 |  | <Create Test case>
| 11 |  | <Prepare Test Data>
| 12 |  | <Peer/Supper review Test case>
| 13 |  | <Fix bug review Test case>
| 14 |  | <Select test case for automated
| 15 |  | <Develop Test scripts/ Test suites>
| 16 |  | <Verify Test scripts/ Test suites>
| 17 |  | <Fix bug scripts/ Test suites>
| 18 |  | <Execute Test/ Run test scripts/ test suites>
| 19 |  | <Re-Test>
| 20 | <Module2>
| 21 |  | <Study SRS>
| 22 |  | <Design test case>
| 23 |  | <Create Test case>
| 24 |  | <Prepare Test Data>
| 25 |  | <Peer/Supper review Test case>
| 26 |  | <Fix bug review Test case>
| 27 |  | <Select test case for automated
| 28 |  | <Develop Test scripts/ Test suites>
| 29 |  | <Verify Test scripts/ Test suites>
| 30 |  | <Fix bug scripts/ Test suites>
| 31 |  | <Execute Test/ Run test scripts/ test suites>
| 32 |  | <Re-Test>
| 33 |  | ….
|  | Total |  |  |  | 0 |  |  | 0 | 0

## 11. Risk & Opportunity
11 | RISK & OPPORTUNITY
<List any risks and opportunities and corresponding mitigation and contingencies that may affect the design or implementation of testing.
For example:
- Test environment
- Test execution
- Product risks
- AutomationTest tools
- Human Resource
- … >
11.1 | Risk Management:
<The following risks have been identified to the plans to achieve the department objectives. These will be managed and updated as during implementation time>
| Risk ID | Risk Source | Risk Category | Risk Description | Probability | Impact | Priority | Risk Status | Last updated date | Trigger | Mitigation | Contingency | Person in charge | Planned end date | Actual end date | Action Status
| R01 | Human resource | Shortage of Human resource |  | High | High | Blocker | Open | dd/mm/yy |  |  |  |  | dd/mm/yy | dd/mm/yy
| R02 | Technical | New Technology |  | High | High | Blocker | Open | dd/mm/yy
11.2 | Opportunity Management:
<The following Opportunities have been identified to the leverage plans to achieve the department objectives. These will be managed and updated as during implementation time>
| Opportunity ID | Opportunity Source | Opportunity category | Opportunity Description | Cost | Expected Benefit | Priority | Opportunity Status | Last updated date | Opportunity action plan |  | Person in charge | Plan end date | Actual end date | Action Status
| Opp01 | Resource | Miscellaneous |  | Low(3) | High(3) | high | Open | dd/mm/yy |  |  |  | dd/mm/yy | dd/mm/yy | Open
Risk Source | OPP Category | OPP sources
Customer | Customer / User Context | Cost
Human resource | Decision Drivers | Customer
Project Characteristics | Deployment | Delivery
Project Dependencies | Development Environment | External
Project Environment | Development Process | Material and equipment
Project Management | Miscellaneous | Quality
Project Requirement | Product Content | Resource
Technical | Project Goals and Objectives | Schedule
| Project Parameters | Scope
Risk Category | Project Team | Technology
Business Processes Complexity | Stakeholder Involvement
Critical Dependencies | Technology
Data Migration Required
Design Difficulty
Existing System Documentation
External driven decisions forced on the project
Hardware Constraints
Implementation Difficulty
Inexperience Customer/End User
Inexperience with Project Process
Inexperience with Project Technology
Insufficient PM Experience
Insufficient business knowledge
Integration Complexity
Lack of Customer Support
Link failure or slow performance
New Technology
Not meeting performance requirements
Parralell development
Physical Facilities
Project Complexity
Risky Dependencies
Shortage of Human resource
Team Spirit and Attitude
Test Ability
Too many requirement changes
Tools Availability
Unclear Acceptance Criteria
Unclear Acceptance criteria and process
Unclear Decision Making Process
Unclear requirements
Unrealistic schedules
Unstable Customer Organization
Vendor/External Support
Weak Customer Involvement
Action Status
Open
In-progress
Passed
Pending
Cancelled
Note on D16: Get info from Risk factor chart
Note on F16: How likely is this risk to occur: Low Medium High
Note on G16: How bad will it be if it happens: Low Medium High
Note on H16: Rank from 1 to 10, 1 is the highest priority. The higher risk exposure is, the higher risk priority is
Note on J16: The date this risk is latest updated
Note on K16: determine how to know if the risk occur so you’ll know when and if put contingencies in place. Do this for High and Medium risks (Risk exposure is 0.0-10)
Note on L16: If >0.5, Mitigation & Contingency plan to be prepared to managed this risk if <=0,3,mitigation actions are not required, but the contingency plan Enter row to add more mitigation as necessary
Note on M16: If >0.5, Mitigation & Contingency plan to be prepared to managed this risk if <=0,3,mitigation actions are not required, but the contingency plan Enter row to add more contingency action as necessary
Note on N16: Person in charge of mitigation/Contingency
Note on O16: If status of this risk is Open, enter Planned end date of Mitigation If status of this risk is Closed, enter Planned end date of Contingency
Note on P16: If status of this risk is Open, enter Actual end date of Mitigation If status of this risk is Closed, enter Actual end date of Contingency
Note on L17: Consider threshold (estimated impact is over Fsoft norm and profanity is high)-->we have plan handling options and based on constrains with customer and project to select the best one.
Note on H24: Priority = impact(1->3)*Probability(1->3) Priority (1->2): low Priority (3->5): Medium Priority (6->9): high
Note on J24: The date this opportunity is latest updated

## Record of Change
12 | RECORD OF CHANGE
No | Effective Date | Version | Change Description | Reason | Reviewer | Approver
1 | 2004-06-20 | 1 | Newly Issued | Add one more test type Regression test | CMMI Core Team | HyTQ
2 | 2004-11-15 | 1.1 | 3.1.10: Add "Define automated test execution schedule here" 5. Milestone: add "…v1.0" | Add regression test type for maintenance project | CMMI Core Team | HyTQ
3 | 2005-06-20 | 1.2 | Add customer constrains on test environment - Add Constrain section - Move Appendix to Test guideline | Fix comment of KPMG from Mar-05 gap analysis (see CMMI-05 action plan) | CMMI Core Team | HyTQ
4 | 2007-05-10 | 1.3 | Add item 1.3: References Correct Heading 3 index Update item 5: add samples for Milestone Task Update item 6: add samples for Deliverables | update the template basing on issues found by training about TP for Test pool | CMMI Core Team | HyTQ
5 | 2007-12-01 | 1.8 | Add new item 1.8: Training needs - Add new item 2.2: 2.2 Acceptance Test Criteria - 3.3: Add Test effort - 5: Add tasks of Unit Test - 6: Add deliverables of Unit test plan | Follow CMMI | CMMI Core Team | HyTQ
6 | 2013-07-20 | 1.9 | SIGNATURE PAGE: "Test Leader", "PTL", "QA", "PM": Replace by "Role" for each project -1.2 Definitions, Acronyms, and Abbreviations: ES, PT/TT, P Voucher, B Voucher.:add new. - 1.5 Scope of testing: Scope of not testing:add new. - 2.1 Test items: Table of the number of test case estimated for testing each item:add new. - 2.2 Acceptance Test Criteria: change "Number/Weighted defects/KLOC" to "Number or Weighted defects/KLOC". - 3 TEST STRATEGY: Guide: Remove because it's described in "Guideline_Test Plan" - 3.1 Test types: Re-Structure document to consistent with Guideline_Test Plan + 3.1.4 Business Cycle Testing; 3.1.6 Load Testing; 3.1.7 Stress Testing; 3.1.8 Volume Testing: remove + 3.1.1 Function Testing: 3.1.1.1 Function Testing, 3.1.1.2 Business Cycle Testing:add new +3.1.4 Performance testing: 3.1.4.1 Performance testing; 3.1.4.2 Load Testing; 3.1.4.3 Stress Testing; 3.1.4.4 Volume Testing: add new - 3.3 Tools: remove - 4.2 System: remove - 4.2 Test management: add new - 5 TEST ENVIRONMENT: add new 5.1 Hardware; 5.2 Software; 5.3 Infrastructure: add new | to fix comment of user | QA | HyTQ
7 | 2018-02-02 | 2.0 | - Update Test Items - Clarify Section “Scope for testing” - Add Define ID/Catalogy for each deliverable - Change Company name: FPT Software Company Ltd -> Fsoft - Add section Test Configuration - Convert template from .doc to .xlsx | Update with comment from SME | CMMI Team | HyTQ
8 | 2020-02-25 | 3.0 | - Sheet 1. Introduction Add Opportunity, Assumptions Update Training needs=>Staff & Training Management - Sheet 3. Test strategy. Add connections or interfaces - Add Sheet 4. Review strategy - Sheet 5. Resource change name to Staff & Training Management Add training Management, Qualification, % Allocate, Start date, End date - Add sheet 10. Test schedule - Add sheet 11. Risk & Opportunity | Follow CMMI5 2.0 | CMMI Team | HuongNTL
9 | 2021-07-28 | 3.1 | - Sheet 2. Requirement for test Update 2.2 Acceptance Test Criteria - Sheet 3. Test strategy Add Static Testing into section 3.1 Test Types Add Test levels table including Test level, Main Task, Entry criteria, Suspension Criteria, Resumption Criteria, Exit criteria into section 3.2 Test Stages - Sheet 4. Review strategy Add Test plan, defect, test basic document to column Review item of the table Update Completion Criteria, Review Type Add column Selection Criteria, Entry Criteria, Suspension Criteria, Resumption Criteria before Completion Criteria - Sheet 9. Deliverables Add Test Procedure Specification | Update following GAP/Recommendations of TMMi framework | TMMi Team | HuongNTL
10 | 2022-04-01 | 3.2 | Update Automation test in sessions of template | Update following Automation test process | NgocCLK, HuongNTL | HuongNTL
11 | 2022-07-15 | 3.3 | - Sheet 3. Test strategy Add Unit Testing into section 3.1 Test Types - Sheet 6. Test enviroment Add Unit test tools into section 6.3 Infrastructure - Sheet 10. Test schedule Add sub-task | Update improving UT phrase | - SEPG: HuongNTL - DevTestMore Team | HuongNTL